DEPARTMENT OF CIVIL AVIATION

SIR SEEWOOSAGUR RAMGOOLAM INTERNATIONAL AIRPORT

PLAINE MAGNIEN

REPUBLIC OF MAURITIUS

Tel: (230) 603 2000

Fax: (230) 637 3164

Email:  civil-aviation@govmu.org

ADDENDUM No 3

Dear All,

Supply, Installation, Testing and Commissioning of Non-Directional Beacon (NDB) and Ancillary Works for Agalega Outer Island, Republic of Mauritius

CAV/QUO/NO. 2 OF 2025-26

With reference to the abovementioned project, please find hereunder replies to the following queries:

Query 1

Quote

Can you provide details for accommodation on the Island?

Unquote

Answer 1

Accommodation on the Island are normally provided by the Outer Islands Development Corporation (OIDC), which is located in the Port Area, Village La Fourche. The rate for room and food arrangements per day per person is 3,000 MUR. The Department of Civil Aviation will coordinate with the OIDC to facilitate regarding accommodation on the Island.  However any costs associated for same has to be borne by the contractor.

Query 2

Quote

Please note that, due to the complex logistics associated with this project and the lead times required for certain items, meeting the Flight Check deadline in May 2026 will not be feasible. Would it be acceptable to DCA to reschedule the Flight Check to the next planned date in November 2026?

Unquote

Answer 2

The flight check of the Non-Directional Beacon (NDB) can be carried out in November 2026, however please note that the commissioning of the Non-Directional Beacon (NDB) includes the flight check and any costs associated for the flight check has to be borne by the contractor.

A BOOJHAWON (Mrs)

for Director of Civil Aviation