FORM B
REPUBLIC OF MAURITIUS

(Ministry of Education and Human Resource)

Indicative Procurement Plan for Financial Year 2026-2027
(Procurement to be undertaken through Open Advertised Bidding)
	Last Updated:


	(To be updated at least every six months)

	S.No.
	Nature of Procurement
	Procurement Details

	Expected Date of launching 

of Bid

	1. 
	Works
	LAN/WIFI in secondary schools
	August/September 2026

	2.
	Goods 
	IT Equipment
	August 2026

	3.
	Goods
	Printing & Stationeries
	November 2026

	4.
	Services
	Recycling/Disposal of E-Waste
	February 2027

	5.
	Work
	Construction and Upgrading of schools
	September 2026

	6.
	Goods
	Juice for National Day Celebrations
	December 2026

	7.
	Goods
	Primary textbooks
	July 2026 –September 2026

	8.
	Goods
	Secondary textbooks
	July 2026 – August 2026

	9.
	Goods
	School requisites (Secondary)- Specialist subjects (Food and Nutrition, chemistry and others/Stationery
	August 2026- September 2026

	10.
	Goods
	School requisites (Primary)- Stationeries
	September 2026

	11.
	Goods
	Furniture for primary and secondary institutions
	September 2026 – October 2026

	12.
	Services
	Supply of Enhanced Meal to ZEP Schools
	Requirements being finalised by User Section. The views of the Ministry of Health are being awaited with respect to the food safety and handling standards to be adopted for the new bidding exercise.
Bids are expected to be launched by 30 September 2026


	13.
	Services
	Transport Services
	Requirements will be submitted by end of September 2026.  Same is being worked out by the User Section.

	14.
	Services
	Security Services
	Requirements will be submitted by end of August 2026.  Same is being worked out by the User Section.

	15.
	Goods
	Procurement of Toners
	Requirements will be submitted by end of August 2026.  Same is being worked out by the User Section.

	16.
	Works 
	Renovation works at Grand Bois GS
	December 2026

	17
	Works
	Electrical Works at Floreal SSS
	August 2026

	18.
	Works
	Upgrading Works at Shrimati Indira Gandhi State Secondary School
	December 2026

	19.
	Works
	Repairs to spalled   concrete & replacement of CIS roof at Riviere des Anguilles GS
	November 2026

	20..
	Works
	Major Upgrading Works (Roofing, false ceiling and waterproofing) at Union Park GS
	November 2026

	21..
	Works
	Construction of a new Pre-Primary Unit (PPU) and emergency fire staircase
	September 2026

	22.
	Works
	Waterproofing works, Painting Works, New canopy to all Blocks, repair to spalling/ Cracks, Upgrading of PPU, Re-roofing of canteen and stands (gradin), Site works (tarmac, sit around, paving blocks), repair to crack boundary wall and any ancillary works at Sir Veerasamy Ringadoo GS

	December 2026

	23.
	Works
	Waterproofing & upgrading works at S. Harilall Vaghjee GS
	December 2026

	24.
	Works
	Relocation and reinstatement of hoarding to create additional playing space, renovation of toilet blocks, replacement and upgrading of classroom openings, repairs to classroom doors, provision of drain covers, removal of loose hanging plywood at the gymnasium, and other associated remedial works to improve the school's safety, functionality, and sanitation at R. Prayag SSS
	December 2026


Date: 17 August 2026
Note:
 The information given is for planning purposes and is subject to revision or cancellation.  It does not constitute a final commitment to buy the goods and services until the procurement process is initiated.
Description to be full enough to give suppliers a reasonable idea of the scope of the work/items required, and to state whether the procurement is a new initiative or arises from expiration of an existing contract.   
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